## GeneralRoadmap
N-System as single node
M-Client reference implementation
N-Client reference implementation
Basic registration and configuration
No scheduling service
Assisted Communications service

## R1-Roadmap
Release 1
R1-A: Design Review	Design Review	8th Nov. 2013
	satnet-2-ReleaseSpecification-R1
	satnet-3-SoftwareArchitecture-R1
	Early Implementation
R1-B: Integration	Design Update			6th December 2013
	satnet-2-ReleaseSpecification-R1 (final)
	satnet-3-SoftwareArchitecture-R1 (final)
	satnet-4-TestReport-R1 (components)
	Software Implementation
	N-System-R1-INTEGRATION
	M-Client-TESTING
	G-Client-TESTING
R1-C: Candidate	Design Update					22nd December 2013
	satnet-4-TestReport-R1 (system)
	Software Implementation
	N-System-R1-CANDIDATE
	M-Client-TESTING
	G-Client-TESTING
R1-D: Testing	Design Update					22nd January 2014
	satnet-4-TestReport-R1 (operational)
	Software Implementation
	N-System-R1-FINAL
	M-Client-TESTING
	G-Client-TESTING