## GeneralRoadmap
N-System as single node
M-Client reference implementation
N-Client reference implementation
Basic registration and configuration
No scheduling service
Assisted Communications service

## R1-Roadmap
Release 1
R1-A: Design Review	Design Review	8th Nov. 2013
	satnet-2-R1-ReleaseSpecification
	satnet-3-R1-SoftwareArchitecture
	Early Implementation
R1-B: Components	Design Update			6th December 2013
	satnet-2-R1-ReleaseSpecification (final)
	satnet-3-R1-SoftwareArchitecture (final)
	satnet-4-R1-Testing (components)
	Software Implementation
	N-System-R1-COMP
	M-Client-TESTING
	G-Client-TESTING
R1-C: Candidate	Design Update					22nd December 2013
	satnet-4-R1-Testing (system)
	Software Implementation
	N-System-R1-CANDIDATE
	M-Client-TESTING
	G-Client-TESTING
R1-D: Operational Testing	Design Update					22nd January 2014
	satnet-4-R1-Testing (operational)
	Software Implementation
	N-System-R1-FINAL
	M-Client-TESTING
	G-Client-TESTING